## Sheet1
Related to | Feature | Original Scope | Final In/Out of Scope | Implemented - Backend | Implemented-Fronend
Design | Well organized interface | Requirement | Done | Done | Done
Profile | Have user profile | Requirement | Done | Done | Done
Course | Display resources related to a course | Challenge | Done | Done | Done
Course | Display the resources related to the assignment | Challenge | Done | Done | Done
Course | Create a course | Requirement | Done | Done | Done
Course | Link for the assignments and course | Requirement | Done | Done | Done
Course | Could be able to assign courses to the students | Requirement | Done | Done | Done
Assignment | Create an assignment | Requirement | Done | Done | Done
Assignment | Set release date | Requirement | Done | Done | Done
Timesheet | Create/ edit the timesheet | Requirement | Done | Done | Done
Timesheet | Show the student avg time spent on the assignment (either from the instructor's input or from previous cohorts) | Requirement | Done | Done | Done
Timesheet | Display how long it took for a particular student to complete the assignment | Requirement | Done | Done | Done
Course | Display everything related to the course (grades, assignments, timesheet) | Requirement | Partially done | Done | Out of scope
Assignment | Will be able to leave a comment on the grading | Requirement | Partially done | Done | Out of scope
Assignment | Could build Rubric for the assignments (not practices) | Requirement | Partially done | Done | Out of scope
Assignment | Grade assignment | Requirement | Partially done | Done | Out of scope
Assignment | Leave comments on students assignment while grading | Requirement | Partially done | Done | Out of scope
Design | Sort options for current ongoing content (prioritization) (sort by due date) | Challenge | Out of scope | Out of scope | Out of scope
Profile | Have preferences (e.g., notifications) | Requirement | Out of scope | Out of scope | Out of scope
Log in | Secure authentication | Requirement | Out of scope | Out of scope | Out of scope
Notifications | Notifications when the assignment is available, grades available, etc. | Requirement | Out of scope | Out of scope | Out of scope
Notifications | Receive an email when the assignment is available, grades available, etc. | Challenge | Out of scope | Out of scope | Out of scope
Notifications | Notifications when a student submits their timesheet/grades /any updates made | Requirement | Out of scope | Out of scope | Out of scope
Course | Course calendar | Challenge | Out of scope | Out of scope | Out of scope
Course | Display next topics coming up | Requirement | Out of scope | Out of scope | Out of scope
Course | Google Drive API interface for resources | Challenge | Out of scope | Out of scope | Out of scope
Course | Can be able to attach files/resources from local machine or online | Challenge | Out of scope | Out of scope | Out of scope
Course | Announcement section, related to upcoming changes or general info | Challenge | Out of scope | Out of scope | Out of scope
Assignment | Forum/posts within a course topic or assignment so all related discussions are in one relevant place (replacing homework help) | Challenge | Out of scope | Out of scope | Out of scope
Assignment | Badges/ rewards on grades and shoutout (i.e., peer support) | Challenge | Out of scope | Out of scope | Out of scope
Assignment | Add shoutout form submission within the assignment | Requirement | Out of scope | Out of scope | Out of scope
Assignment | Rate assignment difficulty level | Requirement | Out of scope | Out of scope | Out of scope
Reporting | Report section for timesheet | Requirement | Out of scope | Out of scope | Out of scope
Reporting | Report section for grades | Requirement | Out of scope | Out of scope | Out of scope
Reporting | Display statistics and key performance indicators | Challenge | Out of scope | Out of scope | Out of scope
Reporting | Print functionality for reports | Challenge | Out of scope | Out of scope | Out of scope