## Sheet1
User | Component | Front end | Back end connection | Front end overall Validation Testing | HTML5 Validation | Anti-tampering Validation | Full Testing
student | Nav | Done | Done | Not applicable | Not applicable | Not applicable | In progress
student | Log in | Done | Done | Done | Done | Done | In progress
student | Course Summary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
student | Homework Summary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
student | Homework/Timesheet | Done | Done | Done | Done | Done | In progress
student | Grades | Not done | Not done | Not done | Not done | Not done | Not done
Instructor | Nav | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Log in | Done | Done | Done | Done | Done | In progress
Instructor | User register | Done | Done | Done | Done | Done | In progress
Instructor | CohortSummary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Cohort (Create) | Done | Done | Done | Done | Done | In progress
Instructor | Cohort (Edit) | Done | Done | Done | Done | Done | In progress
Instructor | Instructor register confirmation | Done | done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Cohort (retire) confirmation | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Manage Courses | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Course (Create) | Done | Done | Done | Done | Done | In progress
Instructor | Course (Edit) | Done | Done | Done | Done | Done | In progress
Instructor | Course (retire) confirmation | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Course Summary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Course (Assign) | Done | Done | Done | Done | Done | In progress
Instructor | Course (edit assigned) | Done | Done | Done | Done | Done | In progress
Instructor | Homework Summary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Homework (remove) confirmation | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Grading Summary | Done | Done | Not applicable | Not applicable | Not applicable | In progress
Instructor | Grades | Not done | Not done | Not done | Not done | Not done | Not done
Instructor | Homework (Create) | Done | Done | Not done | To be tested | Not done | In progress
Instructor | Homework (View/Edit) | Done | Done | Not done | To be tested | Not done | In progress
All | Error page | Not done | Not done | Not applicable | Not applicable | Not applicable | In progress
Last updated 2020-12-08 @ 5:21 pm